## English_form
No. | Objective/Activity | Indicators | Type | Definition | Target (to be deleted) | Data Collection Method | Calculation Formula | Disaggregation | Duration | Data source | Unit | Baseline | 27/Q1 Target | 27/Q2 Target | 27/Q3 Target | 27/Q4 Target | 28/Q1 Target | 28/Q2 Target | 28/Q3 Target | 28/Q4 Target | Final Target
SHM-IMP-0 | Social and economic participation in Sahel Horan Municipality SHM increases, contributing over time to improved household livelihoods, stronger social cohesion, and greater use of the area’s agricultural potential. | Percentage of supported participants who remain engaged in an economic activity 12 months after receiving support | Impact | Percentage of supported participants who remain engaged in an agricultural, food production, food processing, or related income-generating activity 12 months after first receiving support. | ≥70% of supported participants who reach the 12-month follow-up point remain engaged in an economic activity | Municipal participant registry and a short annual follow-up survey or telephone check. Follow-up can focus on participants who have reached 12 months rather than the full participant population. | Number of eligible supported participants remaining engaged at 12 months ÷ number of eligible supported participants assessed at 12 months × 100 | Sex; age group; refugee status; disability; type of support | From month 12 after first support; assessed annually as cohorts reach 12 months and reported at endline. |  | % | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 70
SHM-SO1-0 | Specific Objective 1: Developing Agricultural Technical Skills and Capacity Building | Target groups have improved access to practical agricultural knowledge and technical support | Result | The extent to which youth, women, refugees, farmers and productive households gain access to relevant agricultural training and technical advice. | TBD | - | - | Sex; age; refugee status; disability | Plan period | Post_intervention_form (Q1) | [10 empty] | 0
SHM-SO1-A | Activity A ¦ Developing Technical Partnerships for Applied Agricultural Training |  | Activity
SHM-SO1-A1 |  | Percentage of training (Short-term) participants who report applying knowledge gained | Intermediate result | Percentage of training participants who report using at least one skill or practice gained through the training within six months of completion. | ≥60% of participants reached for follow-up | Short follow-up question through telephone contact or subsequent municipal contact | Participants reporting application ÷ participants followed up × 100 | Sex; age; refugee status; disability; training topic | Annual | Post_intervention_form | % | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 60 | 60
SHM-SO1-A1.2 |  | Number of technical partnerships established or activated for agricultural training and technical support | Output | Number of documented partnerships through which academic, technical, government or national initiative partners provide training, technical advice or related support under the Action Plan. | ≥4 partnerships by June 2027 | Partnership records, agreements, meeting records and activity documentation | Cumulative number of active partnerships contributing to the Plan | Partner type | Years 1–2 and reviewed annually | Partnership_form | # | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 4
SHM-SO1-A1.3 |  | Number of unique participants completing at least one agricultural or food production training programme | Output | Number of unique participants meeting the completion criteria (determin with municipality) | ≥120 participants over the Plan period | Attendance and completion records maintained by training providers and the Municipality | Number of participants meeting completion criteria | Sex; age; refugee status; disability; training topic | Quarterly | Attendance_form | # | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 120
SHM-SO1-B | Activity B ¦ Establishing a Technical Coordination Office to Support Local Agriculture |  | Activity
SHM-SO1-B1 |  | Percentage of farmers and productive households who report benefit from accessing the periodic training and advisory sessions delivered by the technical coordination office | Intermediate result |  | ≥ 70% report benfiting from the advisory sessions |  |  |  | Six months after the setp up of the technical coordination office |  | % | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 70 | 70
SHM-SO1-B1.1 |  | Technical agricultural coordination office established and operational | Milestone | A municipal venue or agreed partner facility is used to provide scheduled agricultural advisory and technical services under a defined pilot arrangement, with a published service schedule and at least one advisory or technical session delivered. | 1 operational office/pilot by Q1 2027 | Municipal decision, service schedule and record of sessions delivered | Achieved / not achieved | Not applicable. | Year 1 | Manual Entry | # | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
SHM-SO1-B1.2 |  | Number of farmers and productive households reaching technical office services | Output | Number of unique farmers and productive households receiving at least one advisory or technical service through the office. | ≥100 unique users over the Plan period | Simple service log maintained by the office | Number of unique users recorded | Sex; age; refugee status; user type | Quarterly after establishment | How to count number of farmers | # | 0 | 0 | 10 | 20 | 20 | 20 | 10 | 10 | 10 | 100
SHM-SO2-0 | Specific Objective 2: Supporting Agricultural Production and Local Food Production | Target groups and local producers are better able to engage in feasible agricultural and food production activities | Result | The extent to which people who receive relevant training and support move into or strengthen agricultural, food production or home-based processing activities. | TBD | - | - | Sex; age; refugee status; disability; activity type | Plan period | Post_intervention_form | [10 empty] | 0
SHM-SO2-C | Activity C ¦ Supporting Small-Scale and Family-Based Agricultural Initiatives Linked to market opprtiunity |  | Activity
SHM-SO2-C1 |  | Percentage of supported production activities still operating six months after support | Intermediate result | Percentage of supported production activities that remain active six months after receiving support. | ≥70% of participants still operating | Short municipal follow-up through telephone contact or site visit where feasible | Active activities at six months ÷ activities reaching six months × 100 | Activity type; crop/product; lead group | Annual | Post_intervention_form | % | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 70 | 70
SHM-SO2-C1.1 |  | Number of production-support partnerships established or activated | Output | Number of documented partnerships through which technical institutions, government entities, food processing facilities or private sector actors provide technical or commercial support to local producers. | ≥3 partnerships by June 2027 | Partnership records and activity documentation | Cumulative number of active partnerships | Partner type | Years 1–2 | Production-support_Partnership_form | # | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3
SHM-SO2-C1.2 |  | Number of pilot agricaultural inisitives launched and connected to wider market opportunity | Output | Number of individual or group production that receive documented municipal facilitation and technical support and have started production or processing. | ≥6 by June 2027 | Activity profile and municipal follow-up record | Cumulative number of supported activities | Activity type; crop/product; women-led; youth-led; refugee participation | From Year 2; cumulative | Linkage_profile | # | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 6
SHM-SO2-C1.3 |  | Number of advisory mentorship sessions provided to the selected initivies | Output |  | TBD | [5 empty] | # | 0 | [8 empty] | 0
SHM-SO2-D | Activity D ¦ Promoting Home-Based and Rural Food Processing Projects
SHM-SO2-D0.1 |  | Number of home-based and rural producers receiving guidance on food safety, licensing, packaging and related requirements | Output | Number of unique producers receiving municipal or partner guidance on requirements relevant to home-based and rural food production. | ≥40 producers over the Plan period | Municipal guidance log | Number of unique producers receiving guidance | Sex; age; refugee status; disability; type of guidance | Quarterly | Completion_form (training title = food processing … etc.) | # | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 40
SHM-SO2-D0.2 |  | Number of training sessions delivered on food processing and related production requirements | Output | Number of training sessions delivered on food safety, food processing, packaging, pricing and marketing for home-based and rural producers. | ≥8 sessions over the Plan period | Attendance sheets and session records | Number of sessions delivered | Topic | Quarterly | registration Form | # | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 8
SHM-SO3-0 | Specific Objective 3: Developing Local Marketing and Rural Markets | Local producers have increased access to markets and commercial opportunities | Result | The extent to which producers gain opportunities to display, promote and sell agricultural and food products through local and external market channels. | TBD | - | - | Sex; age; refugee status; disability; producer type | Plan period | Post_intervention_form | [10 empty] | 0
SHM-SO3-E | Activity E ¦ Organising Open Rural Markets and Seasonal Exhibitions for Agricultural and Food Products |  | Activity
SHM-SO3-E0.1 |  | Number of rural markets and seasonal exhibitions organised or co-organised by the Municipality | Output | Number of documented rural markets, seasonal exhibitions or similar events organised or co-organised by the Municipality to provide local producers with opportunities to display and sell products. | ≥12 events over the Plan period | Event records, announcements and exhibitor lists | Number of documented events | Event type; location | Quarterly | Exhibition_form | # | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 12
SHM-SO3-E0.2 |  | Number of unique local producers participating in supported markets and exhibitions | Output | Number of unique local producers participating in at least one market, exhibition or promotional platform supported by the Municipality. | ≥150 producers over the Plan period | Exhibitor and participant lists linked to the producer registry | Number of unique participating producers | Sex; age; refugee status; disability; producer type | Quarterly | Exhibition_Registration_form | # | 0 |  | 25 | 25 | 25 | 25 | 25 | 25 |  | 150
SHM-SO3-F | Activity F ¦ Supporting Promotion and Marketing of Local Products |  | Activity
SHM-SO3-F0.1 |  | Number of promotional actions/campagins dissemenated through Muncicipality's offical channels (digital platforms, local partnerships and community events) | Output | Number of documented promotional activities delivered through municipal communication channels, community events or product promotion days. | ≥12 actions over the Plan period | Municipal communication and event records | Number of documented actions | Action type; communication channel | Quarterly |  | # | 0 | 0 | 1 | 2 | 2 | 1 | 2 | 2 | 2 | 12
SHM-SO4-0 | Specific Objective 4: Strengthening Municipal Planning, Partnerships and Institutional Coordination | The Municipality has a functioning coordination role that connects residents and producers with relevant programmes, services and partners | Result | The extent to which the Municipality provides a functioning platform for coordination, referrals, partnerships and follow-up related to agriculture and food production. | TBD | - | - | Partner type; service type | Plan period | [11 empty] | 0
SHM-SO4-G | Insitutitional G ¦ Activating the Municipality’s Role as a Platform for Planning, Organisation and Coordination for Agriculture and Food Production |  | Activity
SHM-SO4-G0.1 |  | Local agriculture and food production coordination committee established | Milestone | A committee is formally established with defined membership and responsibilities and holds regular documented meetings. | 1 committee established within six months | Formation decision, membership list, terms of reference and meeting minutes | Achieved / not achieved | Stakeholder type | First six months and quarterly thereafter | Manual Entry Check list / evidance | # | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
SHM-SO4-G0.2 |  | Number of coordination meetings held with relevant partners | Output | Number of documented meetings convened by the Municipality with government, technical, academic, private sector, community and neighbouring municipal partners. | ≥2 meetings per quarter | Meeting minutes and attendance records | Number of documented meetings | Partner type | Quarterly | Manual Entry Check list / evidance | # | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 14
SHM-SO4-G0.3 |  | Number of case studies that demonstrate positive change emerging from muncipality activites | Output | Number of unique residents and producers who receive a documented referral or connection to relevant government programmes, training, financing, technical services or other opportunities through the Municipality. | ≥4 case studies over the Plan period | Referral log | Number of unique people referred or connected | Sex; age; refugee status; disability; service type | Annual |  | # | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 4
SHM-SO4-G0.4 |  | Number of active partnerships contributing to Action Plan activities | Output | Number of partners that have contributed to at least one documented activity, service, referral, training, market opportunity or other agreed contribution during the reporting period. | ≥6 active partners by end of Plan period | Partnership and activity records | Number of partners with at least one documented contribution | Partner type | Semi-annually | Partnership_form | # | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 6
*

## Exhibition_Registration_form
National ID
Participant name
Phone Number
What products do you produce? | Fresh fruits Vegetables Dairy products Meat / livestock products Honey / bee products Olive oil / olives Pickled / preserved products Baked / traditional food products Jams / processed foods Herbs / medicinal plants Handicrafts
What type of producer are you? | Individual farmer/producer Household producer Agricultural cooperative Agricultural association Food-processing business Agricultural enterprise Handicraft producer Women's group/community group Other (specify)
Is this your first time participating in a rural market/exhibition organised or supported by the municipality? | Yes No

## Exhibition_Form
Exhibition / market name
Start Date
End Date
Location
Exhibition duration | Number of days
Capacity (number of booths)
external Sponser (if any)

## Partnership_form
Name of Partner
Contact person
phone
email
Response options (single select): | Government institution (national or local) Public training institute / extension service University / academic institution Private sector company Non-governmental organization (NGO) / civil society organization (CSO) International organization / development partner Financial institution Other (please specify): _______
What is the primary role(s) of this partner in the agricultural training programme? (Select all that apply)” Response options: | Training delivery (provision of training services) Curriculum development and accreditation Funding / financial support Market linkage / job placement Input provision (e.g., seeds, equipment, technology) Community outreach and participant mobilization Technical advisory / extension services Monitoring, evaluation, and learning (MEL) support Logistics and operational support (e.g., venues, transport) Financial services (e.g., loans, grants to beneficiaries) Policy / regulatory support Other (please specify): _______

## Production-support_Partnership_
Name of Partner | (open text)
Contact person | (open text)
Phone | (open text)
Email | (open text)
Partner Type Response options (single select): | Government institution (national or local) Technical institution / research centre Food processing facility / agro-processing company Private sector company (input supplier, trader, agribusiness, etc.) Financial institution Non-governmental organization (NGO) / civil society organization (CSO) International organization / development partner Universities Other (please specify): _______
What is the primary role(s) of this partner in supporting local producers? (Select all that apply) Response options: | Technical advisory / extension services to producers Input provision (e.g., seeds, fertilizer, equipment, technology) Processing / value addition support Market linkage / buyer connections Quality standards, certification, or food safety support Financing / credit / grants to producers Infrastructure or logistics support (e.g., storage, transport, cold chain) Policy / regulatory support Tech readyness Other (please specify): _______

## Completion_form
National_ID
National_ID (validation)
Name
Gender
Age
Phone number
Training title
Training date
What is your current involvement in agriculture? | Farmer (own land) Farmer (working on rented/shared land) Agricultural worker (laborer) Agribusiness owner (e.g., processing, trading) Student (agriculture-related) Not currently working in agriculture
What type of agricultural activity are you involved in? (Select all that apply) | Crop production Livestock Greenhouse farming Food processing Other
did this person meet the completion criteria? | Yes No

## Post_intervention
All | 1. National ID | (9-digit number)
All | 2. Is the respondent the registered participant? | Yes No — spoke to a household member No — could not reach the participant
All | 3. Which follow-up round is this? | Six-month follow-up Twelve-month follow-up Annual check
All | 4. Contact details of this follow-up | Date of contact: ____ Mode: Telephone / Site visit / Municipal office Enumerator name: ____
All | 5. Which municipal support have you received? | Training programme Guidance on food safety, licensing or packaging Production support for a small-scale or family activity Participation in a rural market or exhibition Advisory service from the technical coordination office Referral or connection to a partner or programme
All | 6. Which training(s) did you attend? | <inherited from training registration>
SECTION A — TECHNICAL CAPACITY (SO1)
SO1 | 7. How useful was the training for your agricultural work? | Very relevant Somewhat relevant Not very relevant Not at all relevant
SO1 | 8. Since completing the training, have you applied any of the knowledge or skills you learned? | Yes, regularly Yes, occasionally No
SO1 | 9. If you have not applied the knowledge or skills, what are the main reasons? | Lack of financial resources Lack of equipment or inputs Lack of access to land Lack of employment opportunities Lack of access to markets Lack of time Training was not relevant to my work I need additional training or practice Other
SO1 | 10. As a result of the training, have you changed the way you carry out any agricultural activities? | Yes, significantly Yes, to some extent No
SO1 | 11. What changes have you made? | Changed production methods Improved use of inputs Improved irrigation or water management Improved pest and disease management Improved livestock management Improved post-harvest handling or storage Improved use of equipment or technology Improved record keeping or business practices Other
SO1 | 12. How would you rate your ability to carry out this work on your own, compared with before the training? | Much better than before Somewhat better No change Worse
SO1 | 13. Have you shown or taught any of these practices to another producer or family member? | Yes, more than three people Yes, one to three people No
SO1 | 14. Have you used the municipal agricultural advisory and technical office? | Yes No I was not aware it exists
SO1 | 15. If yes, how many times in the last six months, and for what service? | Number of visits: ____ Service: Technical advice / Input or equipment guidance / Licensing and paperwork help / Market or buyer information / Referral to another entity / Other
SO1 | 16. Was the advice you received useful in practice? | Very useful Somewhat useful Not very useful Not at all useful
SECTION B — PRODUCTION, FOOD SAFETY AND MARKET READINESS (SO2)
B1. Current production status
SO2 | 17. Are you currently carrying out the agricultural or food production activity? | Yes, and I expanded it Yes, at the same level Yes, but reduced No, stopped temporarily No, stopped completely I never started
SO2 | 18. Did you start this activity after receiving municipal support, or did it exist before? | Started after receiving support Existed before, strengthened after support Existed before, no change
SO2 | 19. If you stopped, in which month did you stop and why? | Month and year: ____ Reason: Lack of capital / No market or buyers / Prices too low / Cost of inputs / Water or land access / Health or family reasons / Licensing or regulatory obstacle / Seasonal only, will resume / Other
SO2 | 20. What type of activity is it? | Crop production Livestock Greenhouse farming Home-based food processing Registered food processing Handicraft Other
SO2 | 21. What are your main products? | (Open text, or select from the product list used in the exhibition registration form)
SO2 | 22. Roughly how much do you produce per month now, compared with before the support? | Much more Somewhat more About the same Less Not producing
B2. Food safety, licensing and market requirements
SO2 | 23. Since receiving support, what have you done regarding each of the following? | Health certificate or food safety approval Production or home-business licence or registration Improved hygiene practices in the production area Improved storage or cold-chain handling Proper packaging for the product Product label showing name, ingredients, weight, production and expiry dates A trade name, brand or logo for my products Costing and pricing of the product Social media page or online presence for the product
SO2 | 24. For any item marked "In progress" or "Not yet started", what is the main obstacle? | Cost of fees or equipment Procedures are unclear The office is far or hard to reach Missing documents Waiting on an inspection I do not consider it necessary I do not know where to go Other
SO2 | 25. Do you know which authority to approach for a food safety approval or licence for your product? | Yes, clearly Somewhat No
SO2 | 26. How many people work in this activity, including yourself and unpaid family members? | Total number: ____ Of whom women: ____ Of whom under 30: ____
SECTION C — MARKET ACCESS AND LINKAGES (SO3)
C1. Sales channels
SO3 | 27. Where do you currently sell your products? | I am not selling yet To neighbours, by word of mouth From home Municipal rural market or exhibition Local shops or retailers Wholesaler or trader Food processing facility Cooperative or association Social media or online Buyers outside the governorate Other
SO3 | 28. Which of these channels are new since you received municipal support? | (Same list as Q27; the respondent selects only the new channels)
SO3 | 29. Compared with before the support, are you selling more or less? | Much more Somewhat more About the same Less I am not selling
C2. Markets and exhibitions
SO3 | 30. How many municipal markets or exhibitions have you participated in? | Number: ____
SO3 | 31. At the most recent event, roughly what were your total sales? | Under 50 JOD 50–150 JOD 151–300 JOD 301–500 JOD Over 500 JOD Prefer not to say
SO3 | 32. How many new customers or buyers did you make contact with at that event? | None One to two Three to five More than five
SO3 | 33. What would make these markets more useful for you? | More frequent events Better location Lower or no booth fees More promotion beforehand Better facilities such as shade, electricity or cooling Buyers invited, not only the general public Other
C3. Market linkages
SO3 | 34. Since receiving support, have you established a connection with a buyer, trader, retailer, processing facility or other market actor that led to a sale or an agreement to sell? | Yes No A connection was made but no sale yet
SO3 | 35. For each connection, record the following (repeat up to three times): | Name of buyer, trader or entity: ____ (required) Type: Retailer or shop / Wholesaler or trader / Food processing facility / Restaurant or hotel / Cooperative / Institutional buyer such as a school, hospital or government body / Exporter / Online platform / Other How the connection came about: Through a municipal exhibition or market / Through a municipal referral or the coordination office / Through a partner introduced by the Municipality / Through my own effort, unrelated to municipal support / Other Nature of the arrangement: One-off sale / Repeat sales, no agreement / Verbal agreement / Written contract Still active today: Yes / No / Seasonal
SO3 | 36. What is the main barrier preventing you from selling more? | No steady buyer The price offered is too low Transport costs I cannot produce enough volume I cannot meet quality or certification requirements Packaging or shelf-life Competition Other
SECTION D — CONTINUED ENGAGEMENT (IMPACT) — TWELVE-MONTH ROUND ONLY
Impact | 37. Are you currently engaged in any agricultural, food production, food processing or related income-generating activity? | Yes, as my main activity Yes, as a secondary or seasonal activity No
Impact | 38. In what capacity are you engaged? | Own production on my own land Own production on rented or shared land Own business or processing activity Employed by someone else in agriculture or food production Working in a family activity Not engaged
Impact | 39. If you are not engaged, when did you stop and what was the main reason? | Month and year: ____ Reason: (same option list as Q19)
Impact | 40. Compared with twelve months ago, is your income from this activity higher or lower? | Higher About the same Lower I have no income from it
SECTION E — CLOSING
All | 41. What additional support would help you most in the next year? | More technical training Help with licensing and food safety Equipment or inputs Financing or a small grant Help finding buyers More exhibitions Marketing and branding support Transport or storage Other
All | 42. May we contact you again for a follow-up in six months? | Yes No
All | 43. Enumerator notes | (Open text)

## Linkage_profile
National ID of farmer
name
phone
Partner linkage name
linkage scope
request to linkage :