## English_form
No. | Objective/Activity | Indicators | Type | Definition | Target (to be deleted) | Data Collection Method | Calculation Formula | Disaggregation | Duration | Data source | Unit | Baseline | 27/Q1 Target | 27/Q2 Target | 27/Q3 Target | 27/Q4 Target | 28/Q1 Target | 28/Q2 Target | 28/Q3 Target | 28/Q4 Target | Final Target
KHLD-IMP-0 | Al Khalidiyah Public Park functions as an inclusive shared public space that increases opportunities for interaction, participation, and cooperation between Syrian refugees and the host community | % of surveyed participants reporting that the park provides increased opportunities for interaction and shared community participation between Syrian refugees and the host community | Impact | Evidence from participant feedback, activity records, and municipal observations showing that park activities create opportunities for members of both communities to participate together | Evidence documented annually | Activity feedback forms, attendance records, municipal reports | Qualitative assessment based on documented evidence | Sex, age group, nationality where available | Annual
KHLD-SO1-0 | SO1 ¦ Strengthening Community Partnerships and Institutional Sustainability | % of partner organisations reporting effective coordination and collaboration with the Municipality in implementing park activities | Outcome | Share of surveyed partner organisations reporting that coordination, communication, and joint planning with the Municipality improved during implementation of the Action Plan. | ≥ 70% of surveyed partners | Short annual partner survey or structured interviews | (No. of partners reporting improved coordination ÷ Total partners surveyed) × 100 | Partner type; sex of respondent where applicable | Annually
KHLD-SO1-A | Activity A ¦ Establish a sustainable municipal partnership mechanism
KHLD-SO1-A1 |  | Municipal partnership mechanisms established | Milestone | A functioning coordination arrangement including a designated municipal focal point, stakeholder list, partner communication arrangements, and contribution tracking | One mechanism established | Municipal records | Simple count | N/A (institutional indicator) | Within six months of Plan adoption
KHLD-SO1-A2 |  | Number of coordination meetings held with partners | Output | Meetings conducted with community organisations, cultural institutions, schools, businesses, and other relevant partners, documented through minutes or attendance records | ≥ 4 per year (≥ 12 over the Plan period) | Meeting minutes and attendance sheets | Cumulative count of meetings | By partner type (association / cultural / private sector / educational / donor) | Throughout implementation period
KHLD-SO1-A3 |  | Value and type of contributions mobilised from partners | Output | Financial, in-kind, technical, or volunteer contributions supporting park rehabilitation and activities | Contributions documented annually | Contribution records maintained by Municipality | Simple record of contributions received | Type of contribution and source | Annual review
KHLD-SO1-B | Activity B ¦ Operationalise park coordination arrangements
KHLD-SO1-B1 |  | Park use and activity arrangements established | Milestone | Basic arrangements developed for park use, including activity scheduling, use of spaces, coordination procedures, and communication with partners | One operational arrangement established and updated as needed | Municipal records and activity calendar | Simple count | N/A (institutional indicator) | Within first year
KHLD-SO2-0 | SO2 ¦ Rehabilitation and Activation of Al Khalidiyah Public Park as a Shared Social Space | % of surveyed park users satisfied with the park as a safe and welcoming shared community space | Outocme | Participants providing positive feedback on the suitability of activities and the park as a shared community space | ≥ 60% | Short feedback forms or verbal feedback records | (No of participants rating activities positively ÷ total surveyed) × 100 | Sex, age group, nationality where available | Annually
KHLD-SO2-C | Activity C ¦ Rehabilitation of park facilities
KHLD-SO2-C1 |  | Priority park improvements completed | Output | Rehabilitation or improvement works completed in the designated park section, including seating, play areas, landscaping, sports facilities, lighting, accessibility features, and other agreed improvements | Priority improvements completed according to available resources | Site inspection and completion records | Simple count against agreed rehabilitation list | Facility type | During rehabilitation phase
KHLD-SO2-C2 |  | Volunteer rehabilitation activities conducted | Output | Volunteer campaigns supporting cleaning, planting, minor improvements, and preparation of the park for community use | At least 4 campaigns annually during active implementation | Activity reports and attendance sheets | Number of campaigns conducted | Type of activity | Throughout implementation
KHLD-SO2-D | Activity D ¦ Organise community, cultural, recreational, and sports activities
KHLD-SO2-D1 |  | Number of community activities organised in the park | Output | Cultural, recreational, educational, sports, and community events organised in cooperation with partners | ≥ 12 events during the plan period (≥ 4 annually starting from December 2026) | Event reports and activity calendar records | Cumulative count of events held | Activity type | From December 2026 (after rehabilitation) to September 2029
KHLD-SO2-D2 |  | Number of participants attending events and open days (disaggregated by age and sex) | Output | Number of residents participating in organised park activities | Participation numbers documented for each activity | Attendance records and estimated counts | Total recorded participants | Sex, age group, nationality where available | At every event, December 2026 – September 2029
KHLD-SO3-0 | SO3 ¦ Strengthening Community Participation and Volunteerism | % of volunteers participating in two or more volunteer activities during the implementation period | Outcome | Share of registered volunteers who participate in at least two organised volunteer activities during implementation, demonstrating continued community engagement. | ≥ 40% | Volunteer attendance records | (No. of volunteers participating in two or more activities ÷ Total registered volunteers) × 100 | Sex; age group; nationality; disability | Annual review
KHLD-SO3-E | Activity E ¦ Establish a community coordination committee
KHLD-SO3-E1 |  | Community coordination committees established | Milestone | Voluntary coordination mechanism involving local associations and community organisations supporting park activities | Established/Not Established | Review of founding meeting records | Simple count | Composition by sex and organisation type | By December 2026
KHLD-SO3-F | Activity F ¦ Launch a volunteer programme
KHLD-SO3-F1 |  | Volunteer programme established | Milestone | Volunteer arrangements including volunteer registration, activity roles, and coordination procedures | 1 programme launched by Apr 2027 | Volunteer records | Simple count | N/A (institutional indicator) | Launch by April 2027; continues until September 2029
KHLD-SO3-F2 |  | Number of volunteers recruited | Output | Individuals participating in volunteer activities supporting park rehabilitation, maintenance, and events | ≥ 100 volunteers over the Plan period; of whom ≥ 40% women, ≥ 30% youth (15–24) and ≥ 15% refugees, including persons with disabilities | Volunteer attendance records | Unique count of registered volunteers with ≥ 1 participation | Sex; age group (incl youth 15–24); nationality (Jordanian / Syrian refugee); disability; affiliation (school / university / CSO / community) | From the launch (by April 2027) until September 2029
KHLD-SO3-F3 |  | Number of volunteer action days conducted | Ouput | Organised volunteer action days supporting park maintenance, rehabilitation, community events, or environmental activities. | ≥ 12 action days during the Plan period | Volunteer activity reports and attendance sheets | Cumulative count of action days conducted | Activity type | Throughout implementation
KHLD-SO4-0 | SO4 ¦ Supporting Household Producers through Community Markets and Park Activities | % of participating household producers reporting that community markets increased their opportunities to promote or sell their products | Outcome | Share of participating household producers reporting that participation in community markets increased opportunities to promote products, reach customers, or generate sales. | ≥ 40% | Short follow-up survey after market participation | (No. of producers reporting increased opportunities ÷ Total producers surveyed) × 100 | Sex; nationality; disability; product type | Annual review
KHLD-SO4-G | Activity G ¦ Support home-based micro-enterprises through mentorship and marketing linkages
KHLD-SO4-G1 |  | Number of home-based enterprises completing mentoring / guidance sessions | Output | Home-based enterprises (snacks, refreshments, handicrafts, artisanal goods) whose owners attended the full cycle of brief guidance sessions on small business basics, licensing requirements, hygiene and health & safety standards, marketing and pricing | 20-30 enterprises | Session attendance records | Count of enterprises meeting the completion threshold (attendance at all core sessions) | Sex, age group, nationality and disability of owner; product type | 2027–2028, with enterprise support visits through 2029
KHLD-SO4-G2 |  | Number of home-based enterprises receiving business support | Output | Unique enterprises receiving any form of support under the Plan: guidance sessions, simplified licensing information, referral to training/technical partners, or participation in peer-to-peer exchange networks among entrepreneurs | 20-30 enterprises | Beneficiary log maintained by local associations and the community coordinator | Unique count of supported enterprises | Sex, age group, nationality and disability of owner; type of support | Ongoing starting in 2027
KHLD-SO4-H | Activity H ¦ Organize seasonal community markets and open market days for household producers
KHLD-SO4-H1 |  | Number of community fairs and seasonal market days organised | Output | Market days organised inside Al Khalidiyah Public Park on Fridays, holidays and public occasions, leveraging foot traffic from the adjacent weekly Friday market, with spaces/kiosks for local food, handicrafts and artisanal goods | 10 markets (per Annex 1: JOD 2,000 × 10); pilot phase Apr–Dec 2027, continuing seasonally to 2029 | Event records and activity reports prepared after each market | Cumulative count of market days held | By type/occasion (Friday / holiday / seasonal) | April – December 2027 (pilot phase; seasonal continuation until September 2029
KHLD-SO4-H2 |  | Number of home-based enterprises and vendors participating in park hosted seasonal markets | Output | Household producers and home-based businesses occupying a stall/space in at least one market day Both total participations and unique vendors are tracked, with priority for under-represented groups per the Plan (women, low-income families, youth, refugees, persons with disabilities) | 100-150 vendor participations | Vendor registration sheets completed at each market day | Count of registered vendors per market; unique count across all markets | Sex; age group (incl youth 15–24); nationality (Jordanian / Syrian refugee); disability; product type | On every market day, starting from April 2027
*